## FP Project plan
FileProcessor project plan
Task | Description | est time (hrs) | done
Test harness | Test harness to allow me to run the workflows and make sure the activities all work |  | y
Documentation plan | list all the stuff I need to document |  | y
Documentation | Actually write the docs | 16
Installation plan | plan out what is needed to create the installers for the product |  | y
Copy activity | just needs to be tested |  | y
Delete activity | just needs to be tested |  | y
Move activitiy |  |  | y
Execute activity | just needs to be tested |  | y
Compress activity | needs research & design |  | y
Uncompress activity | needs research & design |  | y
Encrypt activity | needs research & design |  | deffered
Decrypt activity | needs research & design |  | deffered
FileProc service
Code review | make sure I've not left any nasty surprises in there | 8
Test admin tool | tes the admin tool to make sure it works correctly | 4
Test WF designer | make sure it works and produces workflows the engine can run | 4
Test the file processor service | setup the service on the server and hammer the piss out of it to make sure it works | 8
Build the installer |  | 8
Setup store site on GP.com |  | 8
Figure out advertising |  | 8
Hit forums to annouce the release |  | 8
72
720000
960000

## FP documentation plan
Documentation items
Service description | describe how the File Processor service works. Explain how the service finds files and then executes the workflows.
Configuration | describe thzconfiguration file and all of the fields
The admin tool | How to use thzadmin tool to configure the service. how to create workflows how the activities work the string macros that can be used
Developers guide | Describe how the FP service hosts workflows and the services it provides. Explain how to write custom actions for the service Explain how to write 'advanced' workflows for the service

## FP Installation package
Installation tasks
task | Description
Install FP Process | Installs the service and configures it to run on the machine - user has to supply as user id for the service
Install FP Admin tool | Installs the admin tool and developer tools so the service can be configured and new workflows can be created